EVMS Test Metric Specification

Guideline No:

- 29

Test Metric ID:

29A205a

Test Type:

Manual

Attribute/Intent Definition:

29A2:  MR and UB transactions are appropriate and accurately tracked in applicable logs and reports.

Test Definition:

Are UB transactions accurately tracked?

Test Metric:

X = |(Previous period UB + sum (current period UB changes)) - current period UB|

Y = Current period UB

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

20 IPMR/CPR/IPMDAR

20D Current Period UB/ CPD Summary Performance UB

20M Previous Period UB/ CPD Summary Performance UB

41 Budget Log

41D Current Period UB Changes

Assumptions:

- Total rounding error of $1,000 or less due to IPMR/CPR/IPMDAR reporting precision for UB values is not considered a deficiency.

Instructions:

- Identify current period UB from IPMR/CPR Format 1 or IPMDAR CPD Summary Performance; this is the denominator (Y) of the test metric.

- Identify previous period UB from IPMR/CPR Format 1 or IPMDAR CPD Summary Performance and add it to the sum of current period UB changes from the budget log.

- Subtract current period UB from the result in Step 2 and take the absolute value; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Block 11 updated to state rounding error is applied to UB. |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Replaced "discrepancy" with "deficiency" in blk 9 as 3 to be consistent with the overarching 2303-01. | 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 8, 9, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |