EVMS Test Metric Specification

Guideline No:

- 29

Test Metric ID:

29A401a

Test Type:

Automated

Attribute/Intent Definition:

29A4:  Effective controls are in place to restrict changes to work scope and budgets for open work packages.

Test Definition:

Are there changes to open WPs?

Test Metric:

X = Count of prior period open WPs where current month BAC ≠ previous month BAC

Metric Threshold:

X=0

Data Elements Required:

13 EV Cost Tool Data

13C ACWPCUM

13L BAC for WP (current and prior month)

13Q BCWPCUM

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- For discrete WPs: If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- For LOE WPs: If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

- Total comparison difference of $100 (or 1 hour) or less is not considered a deficiency.

- Open WPs have BCWPCUM or ACWPCUM greater than $100.

Instructions:

- Identify and count the number of open WPs from the prior period where current period BAC does not equal the prior period’s BAC; this is the X of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.2 | Add Data Element BCWPCUM |  | 2/21/2019 |
| v3.3 | Added Assumption 3, Deleted Instruction 6, Added Data Element ACWPCUM |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update: Data Elements Required and Instructions |  | 2/22/2020 |
| v3.6 | Update: Test metric and Instructions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13 & updated blk 8 for DECM consistency. Added asm 2 in blk 9 to differentiate discrete from LOE complete. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Added 13AP data element. Updated test metric and instruction to be count only. Changed threshold to 0. | 6, 7, 8, 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |