EVMS Test Metric Specification

Guideline No:

- 29

Test Metric ID:

29A501a

Test Type:

Manual

Attribute/Intent Definition:

29A5:  The PMB is effectively controlled in the freeze period to prevent multiple continuing adjustments with proactive and timely baseline maintenance activities.

Test Definition:

Are PMB changes being controlled in the freeze period per the system description?

Test Metric:

X = Count of sampled PMB changes that are within the freeze period which do not meet the allowable System Description exceptions

Metric Threshold:

X = 0

Data Elements Required:

03 EVM System Description

03H Planning Window/Freeze Period

03T Freeze Period Baseline Change Exceptions

18 Baseline Control Logs

18B Baseline Changes (Selected)

43 Baseline Change Requests

43A Baseline Change Substantiation

Assumptions:

- Test metric is based on a sample of baseline changes.

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Identify the freeze period and freeze period exceptions as described in the system description.

- Identify and count any sampled baseline changes occurring in the freeze period that do not meet the criteria for exceptions.  This is X of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Modified Assumption 1 |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Test Metric, Metric Threshold, Assumptions, and instructions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | Update Instructions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |