EVMS Test Metric Specification

Guideline No:

- 29

Test Metric ID:

29A501c

Test Type:

Automated/Manual

Attribute/Intent Definition:

29A5:  The PMB is effectively controlled in the freeze period to prevent multiple continuing adjustments with proactive and timely baseline maintenance activities.

Test Definition:

Are changes being controlled in the freeze period?

Test Metric:

X = Sum of |(Cost Data sum of BCWSCUR for the current period as of prior period) – (Cost Data sum of BCWSCUR for the current period as of current period)| for the last 2 reporting periods

Y = Sum of |Cost Data sum of BCWSCUR for the current period as of current period| for the last 2 reporting periods

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

02 Accounting/Fiscal Calendar

02C End of period (EOP) dates

13 Cost Data (3 Consecutive Reporting Periods)

13U BCWS (time-phasing)

13X BCWSCUR

Assumptions:

- P1: Period 1 (Current Period)

- P2: Period 2 (Previous Period)

- P3: Period 3 (Month prior to P2)

Instructions:

- Calculate the absolute value of the total BCWSCUR in the Cost Data as reported in P1.

- Calculate the absolute value of the total BCWSCUR in the Cost Data as reported in P2.

- Sum the values calculated in Steps 1 and 2; this is the denominator (Y) of the test metric.

- Calculate Numerator (X) Set 1:

  - Using the Accounting/Fiscal Calendar and P2 Cost Data BCWS time-phased, calculate the total BCWSCUR planned for EOP dates matching P1 reporting date.

  - Using the Accounting/Fiscal Calendar and P1 Cost Data BCWS time-phased, calculate the total BCWSCUR planned for EOP dates matching P1 reporting date.

  - Calculate the absolute value of Step 4.a minus Step 4.b values

- Calculate Numerator (X) Set 2:

  - Using the Accounting/Fiscal Calendar and P3 Cost Data BCWS time-phased, calculate the total BCWSCUR planned for EOP dates matching P2 reporting date.

  - Using the Accounting/Fiscal Calendar and P2 Cost Data BCWS time-phased, calculate the total BCWSCUR planned for EOP dates matching P2 reporting date.

  - Calculate the absolute value of Step 5.a minus Step 5.b values

- Add Set 1 and Set 2; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v6.0 | New metric. Replaces 29A501b which was unable to be executed with IPMDAR. | All | 12/7/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/15/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |