EVMS Test Metric Specification

Guideline No:

- 29

Test Metric ID:

29A601a

Test Type:

Manual

Attribute/Intent Definition:

29A6:  Effective forward planning discipline is maintained with consideration to the size and complexity of the acquisition and the program business rhythm to ensure baseline integrity.

Test Definition:

Is all effort detailed planned within the current rolling wave/freeze period?

Test Metric:

X = Count of PPs/SLPPs where baseline start precedes the next rolling wave cycle

Y = Total count of PPs/SLPPs

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

02 Accounting Fiscal Calendar

02A Accounting Month Dates

03 System Description

03H Planning window/freeze period

13 EV Cost Tool Data

13H BAC

13U BCWS (time-phasing)

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Program unique directives/procedures defines the rolling wave/freeze period process specific to the acquisition contract/program being tested.

- EV Cost Tool data baseline start date is determined by the first Accounting/Fiscal month of non-zero time-phased BCWS.

- Only PPs/SLPPs with BAC > 0 are included in this metric.

Instructions:

- Identify the rolling wave/freeze period process as described in the system description and program directive(s).

- Request the contractor provide the rationale and justification for the development of the rolling wave process. Ensure that the rationale and justification addresses:

  - How was the process developed based on the size and complexity of the program?

  - How do you ensure adequate forward planning is maintained for performance measurement and critical path development?

  - How is the process controlled to maintain baseline integrity?

  - If the rationale provided for the development of the rolling wave process does not adequately address the above questions, then the metric fails: otherwise proceed to Step 3.

- Identify and count all PPs/SLPPs with BAC > 0; this is the denominator (Y) of the test metric.

- Identify the commencement date of the next rolling wave cycle beyond the Freeze Period.

- Identify and count all PPs/SLPPs with BAC > 0 where the baseline start precedes the next rolling wave cycle.  This is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v3.1 | Initial |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Data Elements Required and Assumptions |  | 8/31/2019 |
| v3.5 | Update: Test Step and Assumptions |  | 2/22/2020 |
| v3.6 | Update: Assumptions and Instructions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13 & updated blk 8 for DECM consistency. Update capitalization blk 9. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |