EVMS Test Metric Specification

Guideline No:

- 29

Test Metric ID:

29I402d

Test Type:

Automated/Manual

Attribute/Intent Definition:

29I4:  Work packages planned as LOE must be proactively maintained to ensure that the resulting overall progress assessment is accurate. Budgets for LOE effort must have a sound basis of estimate and be time-phased to properly reflect when the work will be accomplished. If budgets for LOE effort are in the current period (baseline start or finish) and the support work is not necessary to be performed in this period as well as future periods, then the work may be replanned as long as no actual costs for that effort have been previously incurred. If actuals have been incurred, the work may be replanned only in the future periods to reflect when the remaining work is expected to be performed.

Test Definition:

Are budgets for LOE effort based on a sound basis of estimate and time-phased to properly reflect when the work will be accomplished?

Test Metric:

X = Count of LOE CAs/WPs where the last BCWS was 3 reporting periods or more before the last ACWP

Y = Total count of LOE CAs/WPs

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13G ACWPCUR (of selected months)

13H BAC

13U BCWS (time-phasing)

13AA CA UIDs

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Test is conducted at the level where actual costs are collected (CA or WP).

- Test is conducted using one Artifact 13 where data is provided for all reporting periods from contract start and include all records down to the work package level.

- If actual costs cannot be separately identified for LOE and discrete work for commingled control accounts (e.g., through cost collection below the CA level or through charge numbers segmenting costs for LOE and discrete work), then the metric does not apply.

- If the LOE CA/WP has not incurred ACWP, then its last ACWP is the next reporting period.

- Use rounding to the nearest whole number for BAC, time phased BCWS and ACWP.

Instructions:

- Identify all LOE CAs/WPs with BAC > 0, this is the denominator (Y) of the test metric.

- Using the time-phased data, identify the date (reporting period) of the last BCWS.

- Using the time-phased data, identify the date (reporting period) of the last ACWP.

- Count any LOE CAs/WPs where the last BCWS was 3 reporting periods or more before the last ACWP, this is the numerator (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | NEW |  | 12/17/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | Updated blocks 10, 11, and 12. Clarified sampling methodology of Non-LOE tasks/activities & milestones. |  | 5/24/2019 |
| v3.4 | Update: Test Metric, Metric Threshold, Assumptions, and Instructions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v3.6.1 | Removed “sample” from X block 6. Updated instruction wording for clarification. Removed assumptions 1-4 (included in step 1 block 12) |  | 11/02/2020 |
| v4.0 | Update to correct oversight of removing “sample” wording from metric. Add asm 1-3 & update blk 10-2 to align with sampling wording. Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update Data Elements Required and Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |