EVMS Test Metric Specification

Guideline No:

- 30

Test Metric ID:

30A101d

Test Type:

Automated

Attribute/Intent Definition:

30A1:  A change control process exists that controls retroactive changes to previously recorded values for BCWS, BCWP, or ACWP, including approval and explanation.

Test Definition:

Are retroactive changes being made to cumulative BCWS?

Test Metric:

X = Sum of BCWSCUM for WPs where (reporting period BCWSCUM - reporting period BCWSCUR) ≠ prior reporting period BCWSCUM

Y = Total BCWSCUM for all WPs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13W BCWSCUM (current and prior reporting period)

13X BCWSCUR

44 Cost Data Dictionary

Assumptions:

- Differences due to rounding error (within $100 or 1 hour) are not counted as deficiencies.

- PPs and SLPPs are not included.

Instructions:

- Sum BCWSCUM for all WPs in the EV Cost Tool data; this is the denominator (Y) of the test metric.

- Identify and sum of BCWSCUM for all WPs where (reporting period BCWSCUM - reporting period BCWSCUR) ≠ prior reporting changes BCWSCUM; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Changed from count to sum and updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | Added Assumption 3 for clarification |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Deleted unnecessary asm 1 blk 9 & updated asm 2 to specify deficiencies to review. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |