EVMS Test Metric Specification

Guideline No:

- 32

Test Metric ID:

32A101a

Test Type:

Manual

Attribute/Intent Definition:

32A1:  Timely and authorized changes incorporated into the PMB are properly documented and traceable throughout the system in accordance with procedures

Test Definition:

Do the authorized budget changes in the baseline change log trace to the IPMR/CPR/IPMDAR?

Test Metric:

X = |Net change in PMB from baseline change log - Net change in PMB from IPMR/CPR/IPMDAR| for the selected reporting period

Y = |Net change in PMB from baseline change log for the selected reporting period|

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

18 Baseline Control Logs

18J PMB Change (net, current and prior month)

20 IPMR/CPR/IPMDAR

20K Format 1 PMB / CPD Summary Performance PMB BAC (Dollars)

20S Format 3 PMB Change (net, calculated)

Assumptions:

- Selected reporting period is the most recent month with at least one change to the PMB. The selection should be limited to the most recent 12 months of transactions, or to transactions since the most recent test (whichever is less).

- Total rounding error of $1,000 or less due to IPMR/CPR/IPMDAR reporting precision for PMB values is not considered a deficiency.

Instructions:

- Select the most recent month with at least one change to the PMB.

- For the selected reporting period, calculate the net change in the PMB from the baseline change log; the absolute value of this result is the denominator (Y) of the test metric.

- For the selected reporting period, calculate the net change in the PMB. For the CPR/IPMR use Format 3 (Block 6.c (16) – Block 6.a (16)). For the IPMDAR CPD use |(selected period PMB BAC) – (prior period IPMDAR PMB BAC)|.

- Calculate the absolute value of the difference between the results in Step 2 and Step 3; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to v3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Assumptions updated IPMR/CPR rounding error to align with other test metrics |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Replaced "discrepancy" with "deficiency" - to be consistent with the overarching 2303-01. | 9 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 5, 6, 8 | 12/7/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/15/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |