EVMS Test Metric Specification

Guideline No:

- 32

Test Metric ID:

32A102a

Test Type:

Manual

Attribute/Intent Definition:

32A1: Timely and authorized changes incorporated into the PMB are properly documented and traceable throughout the system in accordance with procedures.

Test Definition:

Does the IMS incorporate the latest authorized changes?

Test Metric:

X = Count of sampled baseline change documents where either the baseline start or baseline finish date has been incorrectly incorporated into the IMS

Y = Total count of sampled baseline change documents

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

11 Integrated Master Schedule (IMS)

11G Baseline Finish Date

11J Baseline Start Date

11AP WP/PP/SLPP UIDs

43 Baseline Change Request

43B Baseline Finish Date

43C Baseline Start Date

45 IMS Data Dictionary

Assumptions:

- Test metric is based on a sample of baseline change documents (e.g., BCRs). The sample should be limited to the most recent 12 months of transactions, or to transactions since the most recent test (whichever is less).

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If baseline change documentation does not contain exact dates, then metric is assessed against the same reporting month.

Instructions:

- Select a sample of baseline change documents that include a schedule change; this is the denominator (Y) of the test metric.

- For the sampled baseline change documentation, identify the WPs/PPs/SLPPs impacted by the schedule change(s).  Identify any baseline start and/or baseline finish dates that have been incorporated incorrectly into the IMS.

- Count the number of baseline change documents where at least one baseline date has been incorporated incorrectly into the IMS; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | Update Test Metric |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated blk 8 for consistency. Corrected numbering in blk 10. | 8 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |