EVMS Test Metric Specification

Guideline No:

- 32

Test Metric ID:

32A104a

Test Type:

Manual

Attribute/Intent Definition:

32A1:  Timely and authorized changes incorporated into the PMB are properly documented and traceable throughout the system in accordance with procedures.

Test Definition:

Does the baseline change documentation provide substantiation for the change?

Test Metric:

X = Count of sampled baseline change documents without substantiation

Metric Threshold:

X = 0

Data Elements Required:

18 Baseline Control Logs

18B Baseline Changes (Selected)

43 Baseline Change Request

43A Baseline Change Substantiation

Assumptions:

- Test metric is based on a sample of baseline change documents (e.g., BCRs). The sample should be limited to the most recent 12 months of transactions, or to transactions since the most recent test (whichever is less).

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Determine if the description noted in the baseline change document provides substantiation for the change in accordance with the system description.  Count the baseline change documents that do not have substantiation for the baseline change; this is X of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Test Metric, Metric Threshold, Assumptions, and Instructions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/303/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |